## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities | Develop Android Compatible Mobile App | In-App messaging for Doctors and Patients
Develop iOS Compatible Mobile App | Develop Web Portal application | Security Update | Develop iOS Compatible Mobile App | Mobile App User Interface Refinement
Develop Android Compatible Mobile App | Authentication- Login/Logout | Upgrade Database | Export CSV of Reported Data | Web Portal Redesign
Develop Web Portal application | Web Report of Data (View only no Export) | Send Manual Amber Alerts by Region | Automated Amber Alerts
Upgrade Database | Manual Importing | Basic Data Searching Capability | Automated Integration for Importing
Security Update | Basic Dashboard with heatmap display |  | User Based Preferences- Save Search & Reports
Manual Importing
Automated Integration for Importing
Mobile App User Interface Refinement
Authentication- Login/Logout
Basic Dashboard with heatmap display
Basic Data Searching Capability
Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports
Web Portal Redesign
Export CSV of Reported Data
Send Manual Amber Alerts by Region
Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
Doctors | add the name of patients I have treated | I can add treatments | As a Doctors I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctors | login to the system | I can enter patient treatment information | As a Doctors I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low
CDC Official | push out updates | public can be updated timely | As a CDC Official I can push out updates so that public can be updated timely. | - User can publish and notify the no. of patients who are positive. - User can publish and notify the virus prone areas. - User can publish simple safety measures to be kept in mind.
CDC Official | track test kits delivered to Test Centre | pre-order for future requirements | As a CDC Official I can track test kits delivered to Test Centre so that pre-order for future requirements. | - Comparing it with production rate vs consumption rate. - Make user notify healthcare companies in advance.
Doctors | report successful remedies | government can approve it as valid test | As a Doctors I can report successful remedies so that government can approve it as valid test. | - User can enter before and after reports of patient. - User can track the status of application of successful remedies. - Once approved all doctors will notified about new remedy.
Doctors | Modify appointment | patient recieves best treatment | As a Doctors I can Modify appointment so that patient recieves best treatment. | - User can change time and date assigned to him. - Patient and User will be notified for the change. - Only one time modification can be done.
Healthcare Company | download sale/order report | I can keep record of accounts | As a Healthcare Company I can download sale/order report so that I can keep record of accounts. | - User can select timeline of report. - User can download only in csv format.
Healthcare Company | send invoice | I can receive payments on time | As a Healthcare Company I can send invoice so that I can receive payments on time. | - User must provide complete details of kits made in the provided tenuer. - User cannot edit bill once generated.
Medical Examiner | report the number of deaths caused by the virus | government can take safety measures | As a Medical Examiner I can report the number of deaths caused by the virus so that government can take safety measures. | - Details of patient to be given. - Doctor's detail who was inspecting the patient.
Medical Examiner | add person's location | deaths can be tracked by location | As a Medical Examiner I can add person's location so that deaths can be tracked by location. | - User can select Location - User can add Landmark - notification will be sent to CDC admin.
Patient | provide access to my location | in case I am positive , proper safety measures can be implemeted | As a Patient I can provide access to my location so that in case I am positive , proper safety measures can be implemeted. | - Ask user's permission to access their location. - All nearby Doctors will be notified about patient details.
Patient | Book an apointment with doctor | my treatment can start as soon as possible | As a Patient I can Book an apointment with doctor so that my treatment can start as soon as possible. | - Firstname and Lastname required - Time and date required - Doctor's available slot reqired - user will be assigned nearest doctor
System Administrator | update the product | it functions efficiently | As a System Administrator I can update the product so that it functions efficiently. | - needs to take backup of previous version. - can only update product only if there are certain value of bugs and errors.
System Administrator | shutdown the application | periodic maintainence can be done | As a System Administrator I can shutdown the application so that periodic maintainence can be done. | - Access key required. - Notify all stakeholders about maintainence duration prior via email.
Test Center | notify number of kits required | CDC can allot those kits on time | As a Test Center I can notify number of kits required so that CDC can allot those kits on time. | - User can add numeric value only - User can generate requirement only when kits fall below certain value.
Test Center | notify doctor about patient report | they can take precautionary measure | As a Test Center I can notify doctor about patient report so that they can take precautionary measure. | - User can notify doctor about report in view only mode. - Make user confirm report before sending it.

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 1 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 1 (MVP) | 2 | 2 Total Stories = 4 | 4
Doctors | As a Doctors I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 1 (MVP) | 3 | 3 Total Stories = 3 | 3
Doctors | As a Doctors I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | release 2 | 4 | 4 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered | Release 1 (MVP) | 2 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password | release 2 | 5 | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 1 (MVP) | 1 | 7 Total Stories = 3 |  |  | 3
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | release 3 | 6 | Sum | 10 | 10 | 5
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 1 (MVP) | 3 | Total | 10 | 10 | 5 | 3
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | release 2 | 5 | SUM = TOTAL | TRUE | TRUE | TRUE
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 1 (MVP) | 2
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | release 2 | 5
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 1 (MVP) | 3
Test Center | As a Test Center I can be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low | release 3 | 7
CDC Official | As a CDC Official I can push out updates so that public can be updated timely. | - User can publish and notify the no. of patients who are positive. - User can publish and notify the virus prone areas. - User can publish simple safety measures to be kept in mind. | release 2 | 4
CDC Official | As a CDC Official I can track test kits delivered to Test Centre so that pre-order for future requirements. | - Comparing it with production rate vs consumption rate. - Make user notify healthcare companies in advance. | release 2 | 4
Doctors | As a Doctors I can report successful remedies so that government can approve it as valid test. | - User can enter before and after reports of patient. - User can track the status of application of successful remedies. - Once approved all doctors will notified about new remedy. | release 2 | 5
Doctors | As a Doctors I can Modify appointment so that patient recieves best treatment. | - User can change time and date assigned to him. - Patient and User will be notified for the change. - Only one time modification can be done. | release 2 | 4
Healthcare Company | As a Healthcare Company I can download sale/order report so that I can keep record of accounts. | - User can select timeline of report. - User can download only in csv format. | release 3 | 7
Healthcare Company | As a Healthcare Company I can send invoice so that I can receive payments on time. | - User must provide complete details of kits made in the provided tenuer. - User cannot edit bill once generated. | backlog for future release
Medical Examiner | As a Medical Examiner I can report the number of deaths caused by the virus so that government can take safety measures. | - Details of patient to be given. - Doctor's detail who was inspecting the patient. | Release 1 (MVP) | 1
Medical Examiner | As a Medical Examiner I can add person's location so that deaths can be tracked by location. | - User can select Location - User can add Landmark - notification will be sent to CDC admin. | Release 1 (MVP) | 2
Patient | As a Patient I can provide access to my location so that in case I am positive , proper safety measures can be implemeted. | - Ask user's permission to access their location. - All nearby Doctors will be notified about patient details. | release 2 | 4
Patient | As a Patient I can Book an apointment with doctor so that my treatment can start as soon as possible. | - Firstname and Lastname required - Time and date required - Doctor's available slot reqired - user will be assigned nearest doctor | release 2 | 5
Test Center | As a Test Center I can notify number of kits required so that CDC can allot those kits on time. | - User can add numeric value only - User can generate requirement only when kits fall below certain value. | release 3 | 6
Test Center | As a Test Center I can notify doctor about patient report so that they can take precautionary measure. | - User can notify doctor about report in view only mode. - Make user confirm report before sending it. | release 3 | 7
System Administrator | As a System Administrator I can update the product so that it functions efficiently. | - needs to take backup of previous version. - can only update product only if there are certain value of bugs and errors. | backlog for future release | 0
System Administrator | As a System Administrator I can shutdown the application so that periodic maintainence can be done. | - Access key required. - Notify all stakeholders about maintainence duration prior via email. | backlog for future release | 0

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | 2
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 3
|  | As a Medical Examiner I can report the number of deaths caused by the virus so that government can take safety measures. | 3
| Sprint 2 | As a System Administrator I can give access to the system so that users can access,import, share data.. | 2
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 0.5
|  | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | 5
|  | As a Medical Examiner I can add person's location so that deaths can be tracked by location. | 0.5
| Sprint 3 | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | 5
|  | As a Patient I can change my test results so that the system data is accurate. | 2
|  | As a CDC Official I can track test kits delivered to Test Centre so that pre-order for future requirements. | 1
Release 2 | Sprint 4 | As a Doctors I can login to the system so that I can enter patient treatment information. | 5
|  | As a CDC Official I can push out updates so that public can be updated timely. | 0.5
|  | As a Doctors I can add the name of patients I have treated so that I can add treatments . | 1
|  | As a Patient I can provide access to my location so that in case I am positive , proper safety measures can be implemeted. | 1
|  | As a Doctors I can Modify appointment so that patient recieves best treatment. | 0.5
| Sprint 5 | As a Patient I can Book an apointment with doctor so that my treatment can start as soon as possible. | 1
|  | As a Doctors I can report successful remedies so that government can approve it as valid test. | 2
|  | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | 2
|  | As a Healthcare Company I can reset my password by myself so that that I can login again. . | 1
|  | As a System Administrator I can remove access so that users are not able to access the system. | 3
Release 3 | Sprint 6 | As a Test Center I can notify number of kits required so that CDC can allot those kits on time.. | 3
|  | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | 5
| Sprint 7 | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 2
|  | As a Healthcare Company I can download sale/order report so that I can keep record of accounts. | 0.5
|  | As a Test Center I can notify doctor about patient report so that they can take precautionary measure.. | 5